## Agile Risk Register
ID | Risk Description | Category (Business/Technical/Process/Team) | Probability (H/M/L) | Impact (H/M/L) | Exposure Score (P×I) | Mitigation / Response Strategy | Owner | Status (Open/Mitigated/Closed) | Notes / Updates
R1 | Payment gateway vendor may delay integration | Business | High | High | 9 | Mitigate – negotiate SLA, build fallback option | Product Owner | Open | Vendor discussion scheduled Sprint 2
R2 | New API may not support required data volume | Technical | Medium | High | 6 | Spike in Sprint 1 to test performance | Dev Team | Mitigated | Spike results: scaling required
R3 | Acceptance criteria unclear for order history feature | Process | High | Medium | 6 | Workshop with stakeholders to refine stories | Scrum Master | Open | Planned for Sprint Planning
R4 | Team member with security expertise may leave | Team | Low | High | 3 | Cross-train others, document key processes | Dev Team | Open | Training scheduled Sprint 3